## Sheet1
| General info: | Administrator/Supervisor should be able to assign a batch rather than clicking on the batch. (ie: see attached screen shots). | 20131204 JB - DONE | Comments from Cecila after re-testing
Pit/KFI | Batch # 41359 | Description of issue |  | General info: Alignment still off. Post mark date still maybe an issue. Not satisfied with it being in the middle of PIT pg 1.
1 | PIT PG 1 | Tax amount on line 18 pit pg 1 needs to be calculated with tax rate table "R". | 20131216 JB - Done | Line 18 still is not calculating to the rate table for taxable income.
|  | Bank account routing and checking account number needs to have a verification field. | 20131210 JB - DONE | DONE
|  | Checking and savings both need to be added. |  | DONE
| PIT PG 2 | Account outside the US needs both a Yes box and a No box. |  | DONE
2 | PIT PG 1 | Line 23 needs to be carried over from Pit pg 1 line 22. | 20131210 JB - DONE | DONE
3 | PIT B PG 2 | Move Property factor under 1a column 2 | 20131210 JB - DONE | DONE
| PIT B PG 2 | Move Payroll factor under 2a column 2 | 20131210 JB - DONE | DONE
| PIT B PG 2 | Move Sales Factor under 3a column 2 | 20131210 JB - DONE | DONE
| PIT B PG 2 | Move total factor under column 2 as well | 20131210 JB - DONE | DONE
| PIT B PG 2 | Move average factor under column 2 as well. | 20131210 JB - DONE | DONE
4 | PIT ADJ | Is ok |  | DONE
5 | PIT CR | Is ok |  | DONE
6 | PIT D | Line 1 should have line 38 from Pit 1 carried over as overpayment | 20131210 JB - DONE | DONE
7 | PIT RC | Line 12 from RC Pg 1 should be carried over to line 13 RC Pg 2. | 20131210 JB - DONE | This is done however I forgot to include RC line 1 needs to be carried over from PIT 1 line 5. My mistake.
| PIT RC | Exemptions from PIT Pg 1 should be carried over to line 13 a RC Pg 2. | 20131210 JB - DONE | DONE
| PIT RC | Allow us to key the decimal point. | 20131210 JB - Which decimal point? | This is allowing us to put decimal for line 18b. Done.
8 | PIT S | Is ok |  | DONE
Pit X/Amended | Batch # 41358 | Description of issue
1 | PIT X Pg 1 | Dependant DOB, I put in 1929 and showed up as 2029 | 20131210 JB - Fixed, max two digit year is now this year + 5, so any two digit year beyond that will be 95ish years ago | See screen shot.
2 | PIT X Pg 1 | Include the word "Original Column" and "Amended Column" on rightside above the dollar amounts. | 20131210 JB - There is only one column of textboxes, what label should go where? | If the "Amended Column" could be included above Pg 3 Pit X line 9 on right hand side. See Screen shot.
3 | PIT X Pg 1 | Tax amount on line 18 Pit X Pg 1 needs to be calculated with tax rate table "R". | 20131216 JB - Done | This is working on some of the returns but not all. Not sure why it calculates on some of the returns. Could be the made up amounts?
|  | Bank account routing and checking account number needs to have a verification field. | 20131210 JB - DONE | DONE
|  | Checking and savings both need to be added. |  | DONE
4 | PIT X Pg 2 | Account outside the US needs both a Yes box and a No box. |  | DONE
5 | PIT X B Pg 2 | Move Property factor under 1a column 2 | 20131210 JB - DONE | DONE
| PIT X B Pg 2 | Move Payroll factor under 2a column 2 | 20131210 JB - DONE | DONE
| PIT X B Pg 2 | Move Sales Factor under 3a column 2 | 20131210 JB - DONE | DONE
| PIT X B Pg 2 | Move total factor under column 2 as well | 20131210 JB - DONE | DONE
| PIT X BPg 2 | Move average factor under column 2 as well. | 20131210 JB - DONE | DONE
| PIT X BPg 2 | Line G, election | New | See screen shot Error
6 | PIT ADJ | Is ok |  | DONE
7 | PIT CR | Is ok |  | DONE
8 | PIT D | Line 1 should have line 38 from Pit 2 carried over as overpayment | 20131210 JB - DONE | DONE
9 | PIT RC | Line 13 from RC Pg 1 should be carried over to line 12 RC Pg 1 | 20131210 JB - DONE | DONE
10 | PIT RC | Exemptions from PIT X Pg 1 should be carried over to line 13 a RC Pg 2. | 20131210 JB - DONE | This is done however I forgot to include RC line 1 needs to be carried over from PIT 1 line 5. My mistake.
11 | PIT RC | Low income line 14 should be calculated and auto populated.
S-CORP | Batch # 521 | Description of issue
1 |  | 4 B PG 1 Amended spelled wrong. This field should be auto populated when batch is assigned. No need to key this. | 20131210 JB - fixed spelling, not sure how this would be set on assignment | See screen shot and explanation.
|  | Bank account routing and checking account number needs to have a verification field. | 20131210 JB - DONE | DONE
|  | Checking and savings both need to be added. |  | DONE
2 | S-CORP PG 1 | Account outside the US needs both a Yes box and a No box. |  | DONE
3 | S-CORP PG 1 | Post mark date not entered, where do we enter batch date. | 20131210 JB - not sure what is meant here, timely returns and auto postmark entry are done | Cursor by passes the postmark date not allowing us to key it. Jumps to 5c.
4 | SCHEDULE A | 1 Property factor under E. Property Total | 20131210 JB - DONE | DONE
|  | 2 Payroll factor under F. Payroll Total | 20131210 JB - DONE | DONE
|  | 3 Sales factor under G.Sales Total | 20131210 JB - DONE | DONE
5 | S-CORP SCH B | Is Ok |  | DONE
6 | S-CORP SCH C | Is Ok |  | DONE
7 | S-CORP SCH CR | Is Ok |  | DONE
PTE | Batch # 523 | Description of issue
1 |  | 4 B PG 1 Amended spelled wrong. This field should be auto populated when batch is assigned. No need to key this. | 20131210 JB - fixed spelling, not sure how this would be set on assignment | See screen shot and explanation.
2 |  | Post mark date not entered, where do we enter batch date. | 20131210 JB - not sure what is meant here, timely returns and auto postmark entry are done | Cursor by passes the postmark date not allowing us to key it. Jumps to 4b.
3 | SCHEDULE A | 1 Property factor under E. Property Total | 20131210 JB - DONE | DONE
|  | 2 Payroll factor under F. Payroll Total | 20131210 JB - DONE | DONE
|  | 3 Sales factor under G.Sales Total | 20131210 JB - DONE | DONE
4 | PTE B | Is Ok |  | DONE
CIT | Batch # 525 | Description of issue
1 | CIT Pg 1 | 4a "Original Return" is auto populated when batch is assigned. No need to key this. | 20131210 JB - how would this get auto filled? | See screen shot and explanation.
2 | CIT Pg 1 | Post mark date not entered, where do we enter batch date. | New | Cursor by passes the postmark date not allowing us to key it. Jumps to 4b.
|  | Bank account routing and checking account number needs to have a verification field. | 20131210 JB - DONE | DONE
|  | Checking and savings both need to be added. |  | DONE
|  | Account outside the US needs both a Yes box and a No box. |  | DONE
3 | CIT SCH A | 5 Property factor under E Total Property | 20131210 JB - DONE | DONE
|  | 6 Payroll factor under F Total Property | 20131210 JB - DONE | DONE
|  | 7 Sales factor under G Total Sales | 20131210 JB - DONE | DONE
| CIT B | Is Ok |  | DONE
| CIT C | Is Ok |  | DONE
| CIT D | Is Ok |  | DONE